## Slide 2: Progress Report on Quality Issues
SIPUS – Strengthening of Internationalisation Policies at Universities in Serbia
February 18, 2015
Belgrade, Serbia

## Slide 3
Work package 4 – Quality Plan
To initiate and coordinate internal monitoring and evaluation processes.
Internal evaluation is seen as support and counselling mechanism which aims at ensuring good cooperation, high quality of outputs, and user orientation.
The goal is to outline improvement potentials in order to support the project management in ensuring good project performance and to guarantee that the internationalisation efforts are valuable.

## Slide 4
Evaluation Responsibilities
WP Leader WUS Austria
Gives reports at project meetings on a regular basis.
Provides evaluation tools (e.g. evaluation forms, questionnaires, etc.) and guidelines for partners how to use these evaluation tools.
Gives feedback to the project coordinator and the partners.
Drafts evaluation reports summarising evaluation activities and results.
All project partners
Close cooperation with WUS Austria.
Provision of the requested information completely, faithfully and in time.

## Slide 5
Evaluation Study Visits
Study visits at University of Ghent (June 2014) and University of Graz (September 2014)
Organisation of both study visits, preparatory information and relevance of presented topics was rated very good.
Quality of most speakers and presentations fully met the expectations of the participants and were very useful for their individual work.
Where possible, the participants wished for (even) more practical and interactive work in smaller groups.

## Slide 6
Evaluation Study Visits
Outcomes:
Some participants expect more concrete advice and/or examples on analysing and implementing strategies for internationalisation.
Some participants wish for a more detailed approach to necessary procedures.
Where possible, working documents should be distributed before the study visit.

## Slide 7
Evaluation Questionnaire
Objectives of the SIPUS project
Almost all partners (fully) agree that
Project supports conversion of Serbian Higher Education and Research within EHEA and ERA;
Management of university has recognised importance of and supports internationalisation.
Most partners either agree or are indifferent to the statement that Government of Serbia supports internationalisation of Serbian HEI and provides relevant documents and legislative basis.
Only half of the partners agree that
National level (Ministry and National Councils) have taken
concrete measures by starting to provide relevant documents
and legislative basis.

## Slide 8
Evaluation Questionnaire
Development of Strategies and Policies
All partners either (fully) agree or are indifferent to the statements that
In-depth analysis and assessment report of national framework were presented in a clear and understandable way;
Self-assessments of Serbian universities gave relevant information of status quo;
Comparative study on national legislatives for internationalisation in EU partner countries gave relevant inputs;
Study visits in Ghent and Graz were well organised;
Regarding institutional strategies and policies, my university is carrying out its work as planned.

## Slide 9
Evaluation Questionnaire
Quality Plan, Dissemination, Management
All partners (fully) agree that
Evaluation of study visits was presented in clear and understandable way;
Project website is functional and well organised;
Project management is well organised;
Project coordinators are successful in their work.
All partners either (fully) agree or are indifferent to the statements that
Staff and students at my university are aware of the SIPUS project;
Financial management support is sufficient;
Information about project is well delivered and easily available;
Project has been made visible in the public (one partner does not agree with this statement).

## Slide 10
Evaluation Questionnaire
Statements for specific partners
NIS/Petroleum Industry of Serbia and UNS fully agree that the seminar on internationally related competences of graduates was helpful and reached its targets.
ESN/Erasmus Student Network and UNS fully agree that the project activities so far have improved recognition of ESN and have fostered collaboration between ESN and Serbian HEI.
Ministry, National Councils and UNS do not encounter any obvious obstacles in this project. However, cooperation should be intensified.

## Slide 11
Evaluation Questionnaire
Outstanding features
Work of project coordinators is very successful including
overall project management,
maintenance of project website,
information about project activities.
Internationalisation as such is an important topic and is supported by management of all universities.

## Slide 12
Recommendations
Intensify cooperation with the national level (Ministry and National Councils) through regular meetings, updates, joint workshops, etc.
Take (even) more concrete steps to inform staff and students at your universities to make them aware of the SIPUS project by using university websites, newsletters, dissemination events, etc.
Make the project more visible in the public (in Serbia and abroad) by using different dissemination channels, organising special events, conferences, marketing and PR activities, etc.

## Slide 13
Next evaluation activities
Evaluation of workshop on joint degrees at UNS in March 2015
Evaluation of study visit at University of Pecs in April 2015
Evaluation of study visit at University of Alicante in June 2015
2nd interim evaluation of quality issues at the beginning of 2016
Further evaluation activities on demand

## Slide 14
QUESTIONS?
THANK YOU FOR YOUR ATTENTION!
WUS Austria
Maria Brunnhofer
maria.brunnhofer@wus-austria.org